# Digital Data Application Plan

Applying digital data in receiving and resolving administrative procedures

# I. Objectives

This plan aims to implement the digital transformation of administrative procedures, ensuring efficient and unified execution of document digitization tasks. The key objectives include:

Ensure comprehensive digitization of administrative records and processing results

Strengthen connectivity with citizens through digital support systems

Complete the legal framework for digital administrative procedures by December 2025

Reduce processing time for administrative procedures by at least 30 percent

Improve citizen satisfaction with digital government services

# II. Implementation Content

The implementation is divided into specific tasks assigned to responsible agencies. Each task has defined deliverables, timelines, and coordination requirements.

| No. | Task Name | Lead Agency | Deliverable | Timeline |
| --- | --- | --- | --- | --- |
| 1 | Develop implementation plan | Department of Digital Transformation | Implementation plan document | Q1 2025 |
| 2 | System integration and testing | IT Center | Test report | Q2 2025 |
| 3 | Staff training program | Human Resources Division | Training materials | Q2 2025 |
| 4 | Pilot deployment in 5 provinces | Regional Offices | Pilot evaluation report | Q3 2025 |
| 5 | Full-scale deployment | General Department | Deployment report | Q4 2025 |

# III. Organization and Implementation

All departments and units under the Ministry are responsible for implementing this plan in accordance with their assigned tasks. The following organizational measures apply:

1. Departments and Units

Each department shall develop detailed implementation plans aligned with this master plan. Regular progress reports must be submitted quarterly to the Steering Committee.

2. Steering Committee

The Steering Committee, chaired by the Vice Minister, oversees the overall implementation and resolves cross-departmental issues. Committee meetings are held monthly.

3. IT Center

The IT Center is responsible for technical infrastructure, system integration, and ensuring cybersecurity compliance throughout the digitization process.

4. Monitoring and Evaluation

A monitoring framework with KPIs will track progress. Mid-term evaluation in Q3 2025 will assess whether adjustments are needed. Final evaluation in Q1 2026.

5. Budget Allocation

The total budget for this plan is estimated at VND 15 billion, allocated across infrastructure 40 percent, training 25 percent, operations 20 percent, and contingency 15 percent.

# IV. Risk Assessment and Mitigation

The following risks have been identified along with their mitigation strategies:

Technical Risk: System integration failures between legacy and new platforms. Mitigation: Conduct thorough testing in staging environment before production deployment.

Organizational Risk: Resistance to change from staff accustomed to paper-based processes. Mitigation: Comprehensive training program with hands-on workshops and ongoing support.

Budget Risk: Cost overruns due to scope expansion or vendor price changes. Mitigation: Fixed-price contracts where possible, with 15 percent contingency reserve.

Timeline Risk: Delays in pilot deployment affecting full rollout schedule. Mitigation: Parallel workstreams and buffer time built into the schedule.

Cybersecurity Risk: Data breaches or unauthorized access during digitization. Mitigation: End-to-end encryption, access controls, and regular security audits.

# V. Expected Outcomes

Upon successful implementation of this plan, the following outcomes are expected: a 30 percent reduction in average processing time for administrative procedures, a 50 percent increase in citizen satisfaction scores, complete digitization of all priority administrative records, establishment of a sustainable digital infrastructure, and creation of a replicable model for other government agencies.